## Summary
THE FEATURES MAP · SUMMARY
Baseline v2.21 · 31 August 2026 · companion to the Features Map deck
Measure | Count | What it means
Capability rows | 865 | Across 10 investor journeys, each placed in a reviewed structure.
Live | 524 | 60% of the map. 504 carry a dated walk or ruling.
Planned | 129 | 14% of the map — on the roadmap, not yet shipped.
Gap | 212 | 24% of the map — not built in the product today.
Source |  | Features Map · baseline v2.21 · features_derived.json · verified_live.json · manual_status.json · 31 August 2026

## Coverage
THE FEATURES MAP · COVERAGE BY JOURNEY AND AREA
Every journey, broken into the areas the map nests them in. Gap % is the share of that area's rows that are a Gap.
Journey | Area | Rows | Live | Planned | Gap | Gap %
US Trading | — all areas — | 272 | 150 | 15 | 107 | 39%
| Market | 132 | 102 | 8 | 22 | 16%
| Portfolio | 107 | 25 | 5 | 77 | 71%
| Orders | 28 | 20 | 1 | 7 | 25%
| Watchlist | 5 | 3 | 1 | 1 | 20%
Saudi Market | — all areas — | 197 | 111 | 61 | 25 | 12%
| Market | 108 | 42 | 47 | 19 | 17%
| Portfolio | 59 | 48 | 10 | 1 | 1%
| Orders | 25 | 18 | 3 | 4 | 16%
| Watchlist | 5 | 3 | 1 | 1 | 20%
Mutual Funds | — all areas — | 115 | 78 | 4 | 33 | 28%
| Portfolio | 61 | 37 | 0 | 24 | 39%
| Market | 42 | 37 | 3 | 2 | 4%
| Orders | 7 | 4 | 1 | 2 | 28%
| Watchlist | 5 | 0 | 0 | 5 | 100%
Cash Management | — all areas — | 82 | 61 | 12 | 9 | 10%
| Cash Management | 82 | 61 | 12 | 9 | 10%
Platform | — all areas — | 71 | 49 | 13 | 9 | 12%
| App Widgets | 9 | 7 | 0 | 2 | 22%
| Alert and Notification | 6 | 5 | 1 | 0 | 0%
| Subscription | 5 | 5 | 0 | 0 | 0%
| Calculator | 5 | 4 | 1 | 0 | 0%
| Settings | 5 | 4 | 1 | 0 | 0%
| Family | 4 | 3 | 1 | 0 | 0%
| Engagement | 4 | 0 | 2 | 2 | 50%
| Customization | 4 | 4 | 0 | 0 | 0%
| Auth | 4 | 4 | 0 | 0 | 0%
| Education/Social | 4 | 0 | 2 | 2 | 50%
| Session Duration | 4 | 4 | 0 | 0 | 0%
| Platform | 3 | 1 | 0 | 2 | 66%
| Services | 3 | 0 | 3 | 0 | 0%
| Language | 2 | 2 | 0 | 0 | 0%
| Portfolio Preference | 2 | 2 | 0 | 0 | 0%
| Investment | 2 | 0 | 1 | 1 | 50%
| KYC | 2 | 2 | 0 | 0 | 0%
| Charity | 2 | 1 | 1 | 0 | 0%
| Sharia List Management | 1 | 1 | 0 | 0 | 0%
Robo Advisory | — all areas — | 68 | 37 | 5 | 26 | 38%
| Portfolio | 50 | 24 | 0 | 26 | 52%
| Market | 16 | 11 | 5 | 0 | 0%
| Orders | 2 | 2 | 0 | 0 | 0%
Onboarding | — all areas — | 34 | 20 | 14 | 0 | 0%
| All account types | 15 | 12 | 3 | 0 | 0%
| Corporate | 11 | 0 | 11 | 0 | 0%
| Global | 3 | 3 | 0 | 0 | 0%
| Minor | 3 | 3 | 0 | 0 | 0%
| Saudi | 2 | 2 | 0 | 0 | 0%
LMS/SBL | — all areas — | 13 | 8 | 5 | 0 | 0%
| LMS | 9 | 4 | 5 | 0 | 0%
| SBL | 4 | 4 | 0 | 0 | 0%
IPOs | — all areas — | 9 | 6 | 0 | 3 | 33%
| Subscriptions | 9 | 6 | 0 | 3 | 33%
Crowd Fund | — all areas — | 4 | 4 | 0 | 0 | 0%
| Portfolio | 4 | 4 | 0 | 0 | 0%

## Cross-Product
THE FEATURES MAP · THE FINDING
18 capabilities are a Gap in Mutual Funds, Robo Advisory and US Trading at the same time. Portfolio depth was built for Saudi equity and never extended to anything else ARC sells.
Capability | Live in Saudi Market today? | Closing it means
Finance | Yes — already built | Extend the Saudi surface to the other three products
Gain/Loss | Yes — already built | Extend the Saudi surface to the other three products
Market | Yes — already built | Extend the Saudi surface to the other three products
Orders | Yes — already built | Extend the Saudi surface to the other three products
Overview | Yes — already built | Extend the Saudi surface to the other three products
Portfolio P/L View | Yes — already built | Extend the Saudi surface to the other three products
Statement | Yes — already built | Extend the Saudi surface to the other three products
Transfer | Yes — already built | Extend the Saudi surface to the other three products
Update Avg Cost Price | Yes — already built | Extend the Saudi surface to the other three products
Allocation Tracker | No — build from scratch | New build across all four products
Custom Index Against Benchmark | No — build from scratch | New build across all four products
Goal Tracker | No — build from scratch | New build across all four products
Peer Portfolio Comparison | No — build from scratch | New build across all four products
Personal Investment Manager | No — build from scratch | New build across all four products
Portfolio Analysis | No — build from scratch | New build across all four products
Portfolio Backtesting | No — build from scratch | New build across all four products
Portfolio Health Score | No — build from scratch | New build across all four products
StoryTeller | No — build from scratch | New build across all four products

## Capabilities
THE FEATURES MAP · ALL CAPABILITIES
All 865 rows. Filter any column. Evidence is the dated walk or ruling behind a Live status.
ID | Capability | Journey | Area | Status | Definition | BRD | Evidence date
CM-001 | Mokafaa | Cash Management | Cash Management | Live | Loyalty points → investment portfolios | ARCD 67739 | 2026-08-27
CM-002 | ARC Debit Card | Cash Management | Cash Management | Planned | UCM wallet-linked debit card | ARCD 72647
CM-003 | Buy Round-Up | Cash Management | Cash Management | Planned | Spare change investing on each buy | ARCD 73671
CM-005 | Client Money (Overnight Investments) | Cash Management | Cash Management | Planned |  | ARCD-2647
CM-006 | Cash In | Cash Management | Cash Management | Live
CM-007 | Cash Out | Cash Management | Cash Management | Live
CM-008 | Transfer | Cash Management | Cash Management | Live
CM-009 | Cards and Accounts | Cash Management | Cash Management | Live
CM-010 | Yield & Rewards | Cash Management | Cash Management | Planned
CM-011 | Instant Settlement | Cash Management | Cash Management | Planned
CM-012 | ARC Wallet | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-013 | ARB Account | Cash Management | Cash Management | Gap
CM-014 | Local Bank Transfer | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-015 | Cards | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-016 | From ARC Wallet | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-017 | To ARB Account | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-018 | To Local Bank Account | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-019 | From Saudi Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-020 | To ARB Account | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-021 | To Local Bank Account | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-022 | From US GTN Portfolio | Cash Management | Cash Management | Gap
CM-023 | To ARB Account | Cash Management | Cash Management | Gap
CM-024 | To Local Bank Account | Cash Management | Cash Management | Gap
CM-025 | From US IBKR Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-026 | To ARB Account | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-027 | To Local Bank Account | Cash Management | Cash Management | Gap
CM-028 | From Fund Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-029 | To ARB Account | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-030 | To Local Bank Account | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-031 | From ARC Wallet | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-032 | To Saudi Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-033 | To US IBKR Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-034 | To US GTN Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-035 | To Fund Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-036 | To Crowd Fund Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-037 | To Robo Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-038 | From Saudi Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-039 | To ARC Wallet | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-040 | To Saudi Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-041 | To US IBKR Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-042 | To US GTN Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-043 | To Fund Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-044 | To Crowd Fund Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-045 | To Robo Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-046 | From US IBKR Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-047 | To ARC Wallet | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-048 | To Saudi Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-049 | To US GTN Portfolio | Cash Management | Cash Management | Gap
CM-050 | To Fund Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-051 | To Crowd Fund Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-052 | To Robo Portfolio | Cash Management | Cash Management | Gap
CM-053 | From US GTN Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-054 | To ARC Wallet | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-055 | To Saudi Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-056 | To US IBKR Portfolio | Cash Management | Cash Management | Gap
CM-057 | To Fund Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-058 | To Crowd Fund Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-059 | To Robo Portfolio | Cash Management | Cash Management | Gap
CM-060 | From Fund Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-061 | To ARC Wallet | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-062 | To Saudi Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-063 | To US IBKR Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-064 | To US GTN Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-065 | To Fund Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-066 | To Crowd Fund Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-067 | To Robo Portfolio | Cash Management | Cash Management | Live |  |  | 2026-08-27
CM-068 | Add Card | Cash Management | Cash Management | Live |  |  | 2026-08-31
CM-069 | Delete Card | Cash Management | Cash Management | Live |  |  | 2026-08-31
CM-070 | Cards | Cash Management | Cash Management | Live
CM-071 | Accounts | Cash Management | Cash Management | Live
CM-072 | Add Account | Cash Management | Cash Management | Live |  |  | 2026-08-31
CM-073 | Delete Account | Cash Management | Cash Management | Live |  |  | 2026-08-31
CM-074 | Edit Account | Cash Management | Cash Management | Live |  |  | 2026-08-31
SAU-023 | Buying Power Swap | Cash Management | Cash Management | Planned | Local ↔ International buying power transfer | ARCD-2644
SAU-024 | Instant Settlement | Cash Management | Cash Management | Planned | Same-day or next-day settlement option | ARCD-14352
XJ-030 | ZATCA E-Invoices | Cash Management | Cash Management | Planned | Compliant invoices for wallet + purification — regulatory edge (ARC-unique — no competitor offers this) | #94, #138
XJ-031 | ARB Linked Account | Cash Management | Cash Management | Live | Transfer from Al Rajhi Bank to portfolio | ARCD-2651 | 2026-08-27
XJ-033 | UCM Multi-Currency Wallet | Cash Management | Cash Management | Planned | Additional currencies + improved UI | ARCD-72195
XJ-034 | Multi Virtual IBANs | Cash Management | Cash Management | Planned | Auto-route incoming wire transfers | ARCD-72196
XJ-036 | Apple Pay | Cash Management | Cash Management | Live | Deposit via Apple Pay — digital wallet funding |  | 2026-08-27
XJ-053 | Samsung PAY | Cash Management | Cash Management | Planned |  | ARCD-18747
XJ-069 | Global Last Transaction View | Cash Management | Cash Management | Planned | Cross-product view showing the last transaction across all portfolios and products. | ARCD-60858
CF-001 | Crowdfund Portfolio Home | Crowd Fund | Portfolio | Live | Portfolio view for crowdfunding investment products. |  | 2026-08-11
CF-002 | Crowdfund — Holding Overview | Crowd Fund | Portfolio | Live | Detailed holding view for crowdfund investments. |  | 2026-08-11
CF-003 | Crowdfund — Holdings Filter | Crowd Fund | Portfolio | Live | Filter crowdfund portfolio holdings. |  | 2026-08-11
CF-006 | Crowd Funds Orders | Crowd Fund | Portfolio | Live | Crowd fund order history |  | 2026-08-11
IPO-001 | Individuals Subscription | IPOs | Subscriptions | Live | IPO subscription on Saudi Exchange main market | ARCD-1594 | 2026-08-11
IPO-002 | IPO Details & Status | IPOs | Subscriptions | Live | View listings and subscription status | ARCD-1594 | 2026-08-11
IPO-003 | Individuals Subscription | IPOs | Subscriptions | Live | Parallel market IPO subscription | ARCD-1922 | 2026-08-11
IPO-004 | Institutions Subscription | IPOs | Subscriptions | Gap
IPO-006 | IPO Details & Status | IPOs | Subscriptions | Live |  |  | 2026-08-27
IPO-007 | US IPO | IPOs | Subscriptions | Gap | US IPO subscription capability
IPO-009 | Main Market | IPOs | Subscriptions | Live
IPO-010 | Nomu Market | IPOs | Subscriptions | Live
SAU-019 | Institutions Subscription | IPOs | Subscriptions | Gap | Institutional Nomu subscriptions | ARCD-47866
LMS-008 | Mutual Fund Lending | LMS/SBL | LMS | Planned
LMS-009 | US Lending | LMS/SBL | LMS | Planned
MF-010 | Mutual Fund Margin Lending | LMS/SBL | LMS | Planned | Use fund units as margin collateral | ARCD-8609, ARCD-24456
SAU-003 | Saudi Margin Lending | LMS/SBL | LMS | Live | Digital Sharia-compliant margin lending application | ARCD-1634 | 2026-08-11
SAU-008 | Saudi Auto Margin Approval | LMS/SBL | LMS | Live | Automated compliance/risk approval (ARCD-1923 live; ARCD-85843/ARCD-86236 planned phases) | ARCD 1923, ARCD-85843, ARCD-86236 | 2026-08-11
SAU-009 | Saudi Margin Renewal | LMS/SBL | LMS | Live | Digital renewal at maturity | ARCD-2367 | 2026-08-11
SAU-010 | Saudi Margin Early Payment | LMS/SBL | LMS | Live | Early partial/full repayment | ARCD-2367 | 2026-08-11
SAU-011 | Saudi Margin Phase 2 (Commodities) | LMS/SBL | LMS | Planned | Commodity contractor + promissory notes | ARCD-2424
US-092 | US Margin Lending | LMS/SBL | LMS | Planned | Digital Sharia-compliant margin lending application
LMS-006 | SBL Program | LMS/SBL | SBL | Live | Securities borrowing & lending for yield/short | ARCD-53753 | 2026-08-27
LMS-007 | SBL Digital Acceptance | LMS/SBL | SBL | Live | Digital enrollment and suitability | ARCD-86486 | 2026-08-27
SAU-015 | Short Selling | LMS/SBL | SBL | Live | Sell borrowed securities short | ARCD-53753 | 2026-08-27
US-041 | Short Selling (US) | LMS/SBL | SBL | Live | Short selling capability for US market positions. |  | 2026-08-27
MF-007 | All Fund List | Mutual Funds | Market | Live | Organize catalog by equity/sukuk/etc | ARCD-47782 | 2026-08-11
MF-012 | Private Fund | Mutual Funds | Market | Live | Private equity and private fund products | ARCD-100655 | 2026-08-11
MF-014 | Compare Funds | Mutual Funds | Market | Gap | Side-by-side fund comparison tool | ARCD-98131, ARCD-100521
MF-015 | Top Fund Holders | Mutual Funds | Market | Planned | Show top holders of a mutual fund
MF-016 | Fund Financial Reports | Mutual Funds | Market | Gap | In-app audited financial reports per fund
MF-017 | Fund Recommender | Mutual Funds | Market | Planned | Suitability-based fund recommendations (17+ variants) | ARCD-72386
MF-082 | Saving Fund | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-083 | Dividend Fund | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-084 | Growth Fund | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-085 | Smart Fund | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-086 | Endowment Fund | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-087 | Overview | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-088 | Performance | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-089 | Asset Allocation | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-090 | Dividends | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-091 | Holdings | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-092 | Zakat | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-093 | Documents | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-094 | Fund Performance Chart | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-095 | Dividend Yield | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-096 | Price Update Frequency | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-097 | Fund Category | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-098 | Risk Level | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-099 | Min Subscription | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-100 | Inception Date | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-101 | Inception Price | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-102 | Since Inception Change | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-103 | Redeem | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-104 | Potential Returns | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-105 | Fund Currency | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-106 | Performance vs Benchmark | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-107 | Annual Return | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-108 | Cumulative Return | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-109 | Frequency | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-110 | YTD | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-111 | Past 12 Months | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-112 | Yield | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-113 | Avg Distribution | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-114 | Previous Years Zakat per Unit | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-115 | Calculate Your Zakat | Mutual Funds | Market | Planned
MF-116 | Fund Strategy | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-117 | Geographic Split | Mutual Funds | Market | Live |  |  | 2026-08-27
MF-001 | Subscribe to SAR/USD Fund | Mutual Funds | Orders | Live | SAR-denominated mutual fund subscription | ARCD-47782 | 2026-08-11
MF-002 | USD Fund via SAR Account | Mutual Funds | Orders | Planned | Auto FX conversion for USD fund | ARCD-32980
MF-003 | Cancel Subscription Order | Mutual Funds | Orders | Gap | Cancel pending fund orders
MF-011 | Switch Funds Flow | Mutual Funds | Orders | Live | Switch between fund products |  | 2026-08-11
MF-118 | Edit Order | Mutual Funds | Orders | Gap
MF-119 | Orders History | Mutual Funds | Orders | Live |  |  | 2026-08-27
MF-120 | Customize Orders View | Mutual Funds | Orders | Live |  |  | 2026-08-27
MF-004 | Disable Portfolio | Mutual Funds | Portfolio | Live | Close SAR/USD fund portfolio |  | 2026-08-11
MF-005 | Fund Performance Chart | Mutual Funds | Portfolio | Live | Investment performance over time | ARCD-47782 | 2026-07-16
MF-006 | Dividend History | Mutual Funds | Portfolio | Live | Total dividends received per fund | ARCD-47782 | 2026-08-11
MF-008 | Historical Performance | Mutual Funds | Portfolio | Live | Fund historical performance chart | ARCD-47782 | 2026-08-11
MF-009 | Blocked Amounts Display | Mutual Funds | Portfolio | Live | Show pending buy as blocked amounts | ARCD-48329 | 2026-08-11
MF-020 | Mutual Fund — Holding Overview | Mutual Funds | Portfolio | Live | Detailed holding view for individual mutual fund positions. |  | 2026-08-11
MF-021 | Mutual Fund — Holdings Filter | Mutual Funds | Portfolio | Live | Filter mutual fund portfolio holdings. |  | 2026-08-11
MF-025 | Investment Breakdown (Capital vs Dividends) | Mutual Funds | Portfolio | Live | Split mutual fund total cost into manual contributions vs reinvested dividends, with separate P/L metrics for each | ARCD-91653 | 2026-08-27
MF-027 | Portfolio P/L View | Mutual Funds | Portfolio | Gap | Historical performance chart
MF-028 | Today Gain | Mutual Funds | Portfolio | Live | Day gain/loss for the selected portfolio. |  | 2026-08-27
MF-029 | Market Value | Mutual Funds | Portfolio | Live | Market value of the selected portfolio. |  | 2026-08-27
MF-030 | Total Cash | Mutual Funds | Portfolio | Live | Cash balance of the selected portfolio. |  | 2026-08-27
MF-031 | Total Gain | Mutual Funds | Portfolio | Live | Total gain/loss for the selected portfolio. |  | 2026-08-27
MF-032 | Holding Details | Mutual Funds | Portfolio | Live | Dedicated screen showing one holding in detail: cost, P&L, quantity, avg price, and transactions for that stock |  | 2026-08-27
MF-033 | Update Avg Cost Price | Mutual Funds | Portfolio | Gap | Manual cost price correction
MF-034 | Auto Dividend Reinvest | Mutual Funds | Portfolio | Live | Automatic dividend reinvestment option |  | 2026-08-27
MF-035 | Order List | Mutual Funds | Portfolio | Live | Full list of all submitted orders with status, type, and date. |  | 2026-08-27
MF-036 | Order Details | Mutual Funds | Portfolio | Live | Detail screen for a single order. |  | 2026-08-27
MF-037 | Transaction List | Mutual Funds | Portfolio | Live |  |  | 2026-08-27
MF-038 | Holdings Distribution | Mutual Funds | Portfolio | Live | Breakdown of holdings by sector, market, and currency |  | 2026-08-27
MF-039 | Customize Holdings View | Mutual Funds | Portfolio | Live | Container: customization options for the portfolio view. |  | 2026-08-27
MF-040 | Holdings | Mutual Funds | Portfolio | Live | Customize what columns and data are displayed in the holdings list |  | 2026-08-27
MF-041 | Orders | Mutual Funds | Portfolio | Live | Customize which columns and data are displayed in the orders list. |  | 2026-08-27
MF-042 | Reports | Mutual Funds | Portfolio | Gap | Portfolio reports. Sub-types: Overview, Gain/Loss, Statement, Orders, Transfer, Market, Finance.
MF-043 | Overview | Mutual Funds | Portfolio | Gap | Overview report.
MF-044 | Gain/Loss | Mutual Funds | Portfolio | Gap | Gain/Loss report.
MF-045 | Statement | Mutual Funds | Portfolio | Gap | Statement report.
MF-046 | Orders | Mutual Funds | Portfolio | Gap | Orders report.
MF-047 | Transfer | Mutual Funds | Portfolio | Gap | Transfer report.
MF-048 | Market | Mutual Funds | Portfolio | Gap | Market report.
MF-049 | Finance | Mutual Funds | Portfolio | Gap | Finance report.
MF-050 | Liquidate Portfolio | Mutual Funds | Portfolio | Gap | Bulk liquidation flow
MF-053 | Transfer Funds | Mutual Funds | Portfolio | Gap | In-specie transfer between portfolios
MF-054 | Rename Portfolio | Mutual Funds | Portfolio | Gap | Rename a portfolio.
MF-055 | Copy Portfolio Number | Mutual Funds | Portfolio | Live | Copy the portfolio number to clipboard. |  | 2026-08-27
MF-056 | Hide Balance | Mutual Funds | Portfolio | Live | Mask portfolio balances on screen. |  | 2026-08-27
MF-057 | Portfolio Analysis | Mutual Funds | Portfolio | Gap | Container: portfolio analysis and planning tools.
MF-058 | Peer Portfolio Comparison | Mutual Funds | Portfolio | Gap | Benchmark P&L vs anonymized peers
MF-059 | Portfolio Health Score | Mutual Funds | Portfolio | Gap | Composite quality metric (diversification + risk + perf)
MF-060 | Allocation Tracker | Mutual Funds | Portfolio | Gap | Target vs actual allocation across markets
MF-061 | Goal Tracker | Mutual Funds | Portfolio | Gap | Link assets to financial goals, track progress
MF-062 | StoryTeller | Mutual Funds | Portfolio | Gap | Visual portfolio narratives (1,845 screens)
MF-063 | Daily Brief | Mutual Funds | Portfolio | Gap
MF-064 | Custom Index Against Benchmark | Mutual Funds | Portfolio | Gap
MF-065 | Personal Investment Manager | Mutual Funds | Portfolio | Gap
MF-066 | Portfolio Backtesting | Mutual Funds | Portfolio | Gap | Backtest portfolio allocation against historical market data to evaluate strategy performance.
MF-067 | Share | Mutual Funds | Portfolio | Live | Share a single portfolio view. |  | 2026-08-27
MF-068 | Today Gain | Mutual Funds | Portfolio | Live | Aggregate day gain/loss across every portfolio. |  | 2026-08-27
MF-069 | Market Value | Mutual Funds | Portfolio | Live | Aggregate market value across every portfolio. |  | 2026-08-27
MF-070 | Total Cash | Mutual Funds | Portfolio | Live | Aggregate cash balance across every portfolio. |  | 2026-08-27
MF-071 | Total Gain | Mutual Funds | Portfolio | Live | Aggregate total gain/loss across every portfolio. |  | 2026-08-27
MF-072 | All Holdings List | Mutual Funds | Portfolio | Live | Consolidated holdings list spanning every portfolio. |  | 2026-08-27
MF-073 | Holding Details | Mutual Funds | Portfolio | Live | Holding detail screen reached from the consolidated holdings list. |  | 2026-08-27
MF-074 | Update Avg Cost Price | Mutual Funds | Portfolio | Gap | Manual cost price correction, from the consolidated holding detail.
MF-075 | Orders Across All Portfolios | Mutual Funds | Portfolio | Live | Orders across every portfolio in one list. |  | 2026-08-27
MF-076 | Order Details | Mutual Funds | Portfolio | Live | Order detail screen reached from the consolidated orders list. |  | 2026-08-27
MF-077 | Holdings Distribution Across All Portfolios | Mutual Funds | Portfolio | Live | Holdings distribution across every portfolio. |  | 2026-08-27
MF-078 | Share | Mutual Funds | Portfolio | Live | Share the consolidated all-portfolios view. |  | 2026-08-27
MF-079 | Hide Balance | Mutual Funds | Portfolio | Live | Mask balances on the consolidated all-portfolios view. |  | 2026-08-27
MF-080 | Investment Breakdown (Capital vs Dividends) | Mutual Funds | Portfolio | Live | Split mutual fund total cost into manual contributions vs reinvested dividends, with separate P/L metrics for each |  | 2026-08-27
MF-081 | Auto Dividend Reinvest | Mutual Funds | Portfolio | Live | Automatic dividend reinvestment option |  | 2026-08-27
MF-121 | Watchlist | Mutual Funds | Watchlist | Gap | Dedicated US market watchlist with real-time prices and daily change.
MF-122 | Watchlist Story | Mutual Funds | Watchlist | Gap | Instagram-style story view for US watchlist stocks with key metrics.
MF-123 | Auto-Watchlist on Buy | Mutual Funds | Watchlist | Gap | Automatically add US stocks to watchlist when purchased.
MF-124 | Watchlist — Edit / Reorder | Mutual Funds | Watchlist | Gap | Edit watchlist: reorder, remove, or rename watchlists.
MF-125 | Multi Views | Mutual Funds | Watchlist | Gap
ONB-001 | Digital Account Opening (Saudi) | Onboarding | All account types | Live | Standard onboarding for Saudi nationals via SuperApp | ARCD-47480 | 2026-08-11
ONB-003 | Update National Address | Onboarding | All account types | Live | Self-service national address update | ARCD-14242 | 2026-08-11
ONB-004 | Session Upgrade & OTP | Onboarding | All account types | Live | One-time session upgrade for high-value actions | ARCD-84906 | 2026-08-11
ONB-007 | Expired ID Handling | Onboarding | All account types | Live | Detect expired IDs and route to renewal | ARCD-99958 | 2026-08-11
ONB-017 | Face ID / Biometric Setup | Onboarding | All account types | Live | 3-step Face ID setup flow |  | 2026-08-11
ONB-019 | Non-ARB Bank Account Entry | Onboarding | All account types | Live | External bank details for non-ARB clients | ARCD-98292 | 2026-08-11
ONB-020 | KYC Confirmation Screens | Onboarding | All account types | Live | Success/error modals across KYC |  | 2026-08-11
ONB-022 | Progress Indicator / Stepper | Onboarding | All account types | Live | Visual stepper in onboarding — reduces drop-off |  | 2026-08-11
ONB-023 | Pre-filled KYC from National ID | Onboarding | All account types | Live | Pre-fill fields from ID data — faster registration |  | 2026-08-11
ONB-025 | First Engagement | Onboarding | All account types | Live | Guided first-trade experience post-signup (3,766 screens) |  | 2026-08-11
ONB-026 | Fast Onboarding | Onboarding | All account types | Planned | Streamlined reduced-step KYC (364 screens)
ONB-039 | Guest Mode | Onboarding | All account types | Planned | Allows users to browse the app without an account in a limited-access mode. | ARCD-75522
ONB-040 | Tutorials | Onboarding | All account types | Live | In-app tutorial screens teaching trading basics, app navigation, and key features. |  | 2026-08-11
ONB-043 | Data Consent Management | Onboarding | All account types | Live |  |  | 2026-08-11
XJ-024 | Guest Mode (Extended) | Onboarding | All account types | Planned | 8,012 screens designed for discovery mode | ARCD-75522
ONB-028 | Corporate — Other Local Entities | Onboarding | Corporate | Planned | Onboarding flow for non-company corporate entities (associations, government bodies, etc.) | ARCD-2958
ONB-029 | Corporate — Approval Flow | Onboarding | Corporate | Planned | Approval screen shown when a corporate account application is accepted. | ARCD-2958
ONB-030 | Corporate — Under Review | Onboarding | Corporate | Planned | Status screen shown while a corporate account application is under review. | ARCD-2958
ONB-031 | Corporate — Additional Requirements | Onboarding | Corporate | Planned | Screen prompting the corporate applicant to upload additional required documents. | ARCD-2958
ONB-032 | Corporate — Rejected | Onboarding | Corporate | Planned | Notification screen when a corporate account application is rejected. | ARCD-2958
ONB-033 | Corporate — Local Company Onboarding | Onboarding | Corporate | Planned | Full onboarding flow for local Saudi companies including CR validation and entity details. | ARCD-2958
ONB-034 | Corporate — Profile & Settings | Onboarding | Corporate | Planned | Corporate user profile and account settings management screens. | ARCD-2958
ONB-035 | Corporate — Requirements Upload | Onboarding | Corporate | Planned | Document upload screen for corporate onboarding requirements and supporting files. | ARCD-2958
ONB-036 | Corporate — Terms & Conditions | Onboarding | Corporate | Planned | Terms and conditions acceptance screen for corporate account opening. | ARCD-2958
ONB-037 | Corporate — Status Tracking | Onboarding | Corporate | Planned | Application status tracker allowing corporate users to monitor their onboarding progress. | ARCD-2958
ONB-038 | Corporate — Pending Actions | Onboarding | Corporate | Planned | Pending action items dashboard for corporate users requiring attention. | ARCD-2958
ONB-005 | GCC Customer Onboarding | Onboarding | Global | Live | Onboarding for GCC nationals with ID + face verification | ARCD-47480 | 2026-08-11
ONB-008 | GCC Customer ID Update | Onboarding | Global | Live | Existing GCC clients update expired docs | ARCD-47480 | 2026-08-11
ONB-009 | Foreign Customer ID Verification | Onboarding | Global | Live | Real-time ID + face scan for foreign customers | ARCD-79680 | 2026-08-11
ONB-002 | Minor Account Onboarding | Onboarding | Minor | Live | Guardian-initiated onboarding for minor children — Saudi nationals only (ARB or non-ARB) | ARCD 45978 | 2026-08-11
ONB-012 | Guardian Trading for Minor | Onboarding | Minor | Live | Execute trades on behalf of a minor — Saudi nationals only |  | 2026-08-11
ONB-027 | Minor Account + Guardian Controls | Onboarding | Minor | Live | Granular custodian controls for minor accounts — Saudi nationals only; ARC-unique (no competitor) | #8-10 | 2026-08-11
ONB-006 | Family Onboarding | Onboarding | Saudi | Live | Digital onboarding for family members — Saudi nationals only (ARB or non-ARB) | ARCD-26191 | 2026-08-11
ONB-021 | Family Members Overview | Onboarding | Saudi | Live | Home screen showing linked family accounts |  | 2026-08-11
XJ-059 | Global Notification | Platform | Alert and Notification | Planned |  | ARCD-75525, ARCD-20124
XJ-102 | News | Platform | Alert and Notification | Live |  |  | 2026-08-31
XJ-103 | Orders | Platform | Alert and Notification | Live |  |  | 2026-08-31
XJ-104 | Cash | Platform | Alert and Notification | Live |  |  | 2026-08-31
XJ-105 | Portfolio | Platform | Alert and Notification | Live |  |  | 2026-08-31
XJ-106 | Market | Platform | Alert and Notification | Live |  |  | 2026-08-31
XJ-109 | Portfolio | Platform | App Widgets | Live |  |  | 2026-08-31
XJ-110 | Watchlist | Platform | App Widgets | Live |  |  | 2026-08-31
XJ-111 | Stock | Platform | App Widgets | Live |  |  | 2026-08-31
XJ-112 | Fund | Platform | App Widgets | Live |  |  | 2026-08-31
XJ-113 | Robo | Platform | App Widgets | Live |  |  | 2026-08-31
XJ-114 | Saudi News | Platform | App Widgets | Live |  |  | 2026-08-31
XJ-115 | Orders | Platform | App Widgets | Live |  |  | 2026-08-31
XJ-116 | Top Movers | Platform | App Widgets | Gap
XJ-117 | US News | Platform | App Widgets | Gap
ONB-018 | Change Password | Platform | Auth | Live | Self-service password update |  | 2026-08-31
XJ-072 | Set password | Platform | Auth | Live |  |  | 2026-08-31
XJ-073 | Face ID | Platform | Auth | Live |  |  | 2026-08-31
XJ-074 | MPIN | Platform | Auth | Live |  |  | 2026-08-31
XJ-001 | Zakat Calculator | Platform | Calculator | Live | Zakat on investment holdings | ARCD-1283 | 2026-08-31
XJ-048 | Purification Calculator | Platform | Calculator | Planned | Sharia purification amount calculation | ARCD-1096
XJ-054 | Investment Calculator | Platform | Calculator | Live |  |  | 2026-08-31
XJ-067 | Dividend Calculator | Platform | Calculator | Live | Interactive dividend income estimator |  | 2026-08-31
XJ-108 | Average Cost Calculator | Platform | Calculator | Live |  |  | 2026-08-31
XJ-044 | Charity / Donation Screen | Platform | Charity | Live | Charity investment offerings |  | 2026-08-11
XJ-051 | Auto Zakat | Platform | Charity | Planned |  | ARCD-72339
XJ-094 | Order View | Platform | Customization | Live |  |  | 2026-08-31
XJ-095 | Portfolio Holding | Platform | Customization | Live |  |  | 2026-08-31
XJ-096 | Home Page | Platform | Customization | Live |  |  | 2026-08-31
XJ-097 | Market Page | Platform | Customization | Live |  |  | 2026-08-31
ONB-044 | How-To Guides | Platform | Education/Social | Planned | Step-by-step how-to guides (deposit, trade)
SAU-099 | Social / Copy Trading | Platform | Education/Social | Planned | Follow & replicate professional traders | ARCD-72352
XJ-021 | Education | Platform | Education/Social | Gap | Interactive tutorials for new users
XJ-052 | Mock Trading | Platform | Education/Social | Gap
XJ-037 | Bundle Benefits (ARG) | Platform | Engagement | Planned | Al Rajhi Group-wide fee discounts | ARCD 18697
XJ-039 | Spin the Wheel | Platform | Engagement | Planned | Gamified commission discounts at milestones | ARCD-16056, ARCD-97344
XJ-042 | Referral / Gift Campaigns | Platform | Engagement | Gap | Date-specific gift campaigns to segments | ARCD-42865, ARCD-23093
XJ-045 | Social Community Feed | Platform | Engagement | Gap | Stock-specific discussions + sentiment tracking
ONB-011 | Minor Trading Restrictions | Platform | Family | Planned | Guardian configures trade limits on minor accounts | ARCD 45978
XJ-078 | Minor Onboarding | Platform | Family | Live |  |  | 2026-08-31
XJ-079 | Switch to Minor | Platform | Family | Live |  |  | 2026-08-31
XJ-080 | Switch to Main Account | Platform | Family | Live |  |  | 2026-08-31
XJ-038 | Smart Saving Plan | Platform | Investment | Gap | Bulk ARB deposits to mutual funds
XJ-057 | Subscription Engine | Platform | Investment | Planned |  | ARCD-2632
XJ-087 | Update KYC | Platform | KYC | Live |  |  | 2026-08-31
XJ-088 | Edit KYC | Platform | KYC | Live |  |  | 2026-08-31
XJ-075 | Arabic | Platform | Language | Live |  |  | 2026-08-31
XJ-076 | English | Platform | Language | Live |  |  | 2026-08-31
SAU-006 | TILA | Platform | Platform | Live | Real-time vs delayed price management | ARCD-2933 | 2026-08-11
XJ-049 | ARC Chatbot | Platform | Platform | Gap |  | ARCD-86222
XJ-068 | Cross-Product Gain-Loss Chart | Platform | Platform | Gap | Unified gain-loss chart showing performance across all ARC products (local, international, funds). | ARCD-60382
XJ-098 | Saudi Market | Platform | Portfolio Preference | Live |  |  | 2026-08-31
XJ-099 | Mutual Fund | Platform | Portfolio Preference | Live |  |  | 2026-08-31
SAU-016 | Tadawulaty SSO | Platform | Services | Planned | Single sign-on to Edaa platform | ARCD-22970
XJ-004 | ZATCA Purification Invoice | Platform | Services | Planned | Compliant e-invoice for purification | ARCD-14553
XJ-040 | Prepaid Commission Bundle | Platform | Services | Planned | Commission-free trading period subscription | ARCD-17031
XJ-089 | 15 Min | Platform | Session Duration | Live |  |  | 2026-08-31
XJ-090 | 30 Min | Platform | Session Duration | Live |  |  | 2026-08-31
XJ-091 | 45 Min | Platform | Session Duration | Live |  |  | 2026-08-31
XJ-092 | 60 Min | Platform | Session Duration | Live |  |  | 2026-08-31
XJ-017 | Always On Display | Platform | Settings | Live | Keep screen on while using app |  | 2026-08-11
XJ-018 | Index Feed Bar Settings | Platform | Settings | Live | Configure live market ticker bar |  | 2026-08-11
XJ-061 | Dark/Light Theme | Platform | Settings | Live |  |  | 2026-08-11
XJ-064 | Font Size | Platform | Settings | Live |  |  | 2026-08-11
XJ-070 | Portfolio-to-Mobile Linking | Platform | Settings | Planned | Link customer portfolio access to a single verified mobile number for security. | ARCD-83211
XJ-101 | View Only Shariah Compliant Stocks (On/Off) | Platform | Sharia List Management | Live |  |  | 2026-08-31
XJ-081 | Saudi Live Price | Platform | Subscription | Live |  |  | 2026-08-31
XJ-082 | US Live Price | Platform | Subscription | Live |  |  | 2026-08-31
XJ-083 | Options and Live Prices | Platform | Subscription | Live |  |  | 2026-08-31
XJ-084 | Market Depth | Platform | Subscription | Live |  |  | 2026-08-31
XJ-085 | My Subscriptions | Platform | Subscription | Live |  |  | 2026-08-31
RBO-002 | Create Investment | Robo Advisory | Market | Live | New portfolio with risk profile assignment | ARCD-85842 | 2026-08-11
RBO-006 | Try-Before-Invest Simulator | Robo Advisory | Market | Live | Pre-built strategies with simulation mode |  | 2026-08-11
RBO-008 | Investment Strategies | Robo Advisory | Market | Live | Compare conservative vs aggressive vs balanced |  | 2026-08-11
RBO-012 | Safe Investment | Robo Advisory | Market | Live |  |  | 2026-08-27
RBO-013 | Medium Investment | Robo Advisory | Market | Live |  |  | 2026-08-27
RBO-014 | High Risk Investment | Robo Advisory | Market | Live |  |  | 2026-08-27
RBO-015 | Expected Avg Return | Robo Advisory | Market | Planned
RBO-016 | Expected Dividend Yield | Robo Advisory | Market | Planned
RBO-017 | Min. Subscription | Robo Advisory | Market | Live |  |  | 2026-08-27
RBO-018 | Asset Composition | Robo Advisory | Market | Live |  |  | 2026-08-27
RBO-020 | Overview | Robo Advisory | Market | Planned
RBO-021 | Historical Annual Gain | Robo Advisory | Market | Planned
RBO-022 | Historical Annual Loss | Robo Advisory | Market | Planned
RBO-023 | Risk Level | Robo Advisory | Market | Live |  |  | 2026-08-27
RBO-029 | Profile | Robo Advisory | Market | Live |  |  | 2026-08-27
RBO-031 | Plan Distribution | Robo Advisory | Market | Live |  |  | 2026-08-27
RBO-001 | Risk Confirmation | Robo Advisory | Orders | Live | Suitability questions + risk profile assessment | ARCD-22648, ARCD-93704 | 2026-08-11
RBO-063 | Transaction Details | Robo Advisory | Orders | Live |  |  | 2026-08-27
RBO-003 | Withdraw | Robo Advisory | Portfolio | Live | Native withdrawal from Robo portfolio | ARCD-85842 | 2026-08-11
RBO-004 | Mashura Reports | Robo Advisory | Portfolio | Gap | Robo advisory reporting screens | ARCD-85842
RBO-005 | Goal-Based Portfolio (Full) | Robo Advisory | Portfolio | Gap | End-to-end goal-based investment product, not just tracker | ARCD-85842
RBO-010 | Mashura — Holding Overview | Robo Advisory | Portfolio | Live | Detailed holding view for robo advisory positions. | ARCD-85842 | 2026-08-11
RBO-011 | In-line Allocation Editing | Robo Advisory | Portfolio | Gap | Add an asset or change its allocation weight directly from the portfolio view.
RBO-032 | Market Value | Robo Advisory | Portfolio | Live |  |  | 2026-08-27
RBO-033 | Total Cost | Robo Advisory | Portfolio | Live |  |  | 2026-08-27
RBO-035 | Performance Chart | Robo Advisory | Portfolio | Live |  |  | 2026-08-27
RBO-037 | Holdings Table | Robo Advisory | Portfolio | Live |  |  | 2026-08-27
RBO-038 | Transactions | Robo Advisory | Portfolio | Live |  |  | 2026-08-27
RBO-039 | Allocation | Robo Advisory | Portfolio | Gap
RBO-040 | Dividends | Robo Advisory | Portfolio | Live |  |  | 2026-08-27
RBO-041 | Zakat | Robo Advisory | Portfolio | Live |  |  | 2026-08-27
RBO-042 | Automatic Zakat Payment | Robo Advisory | Portfolio | Live |  |  | 2026-08-27
RBO-043 | Zakat Amount Per Unit | Robo Advisory | Portfolio | Live |  |  | 2026-08-27
RBO-045 | Add Cash | Robo Advisory | Portfolio | Live |  |  | 2026-08-27
RBO-047 | Avg Cost | Robo Advisory | Portfolio | Live |  |  | 2026-08-27
RBO-048 | Gain/Loss % | Robo Advisory | Portfolio | Live |  |  | 2026-08-27
RBO-049 | Today Gain | Robo Advisory | Portfolio | Live |  |  | 2026-08-27
RBO-064 | Portfolio P/L View | Robo Advisory | Portfolio | Gap | Historical performance chart
RBO-065 | Today Gain | Robo Advisory | Portfolio | Live | Day gain/loss for the selected portfolio. |  | 2026-08-27
RBO-066 | Total Cash | Robo Advisory | Portfolio | Live | Cash balance of the selected portfolio. |  | 2026-08-27
RBO-067 | Total Gain | Robo Advisory | Portfolio | Live | Total gain/loss for the selected portfolio. |  | 2026-08-27
RBO-068 | Holding Details | Robo Advisory | Portfolio | Live | Dedicated screen showing one holding in detail: cost, P&L, quantity, avg price, and transactions for that stock |  | 2026-08-27
RBO-069 | Update Avg Cost Price | Robo Advisory | Portfolio | Gap | Manual cost price correction
RBO-070 | Auto Dividend Reinvest | Robo Advisory | Portfolio | Gap | Automatic dividend reinvestment option
RBO-073 | Customize Holdings View | Robo Advisory | Portfolio | Live | Container: customization options for the portfolio view. |  | 2026-08-27
RBO-074 | Holdings | Robo Advisory | Portfolio | Live | Customize what columns and data are displayed in the holdings list |  | 2026-08-27
RBO-076 | Reports | Robo Advisory | Portfolio | Gap | Portfolio reports. Sub-types: Overview, Gain/Loss, Statement, Orders, Transfer, Market, Finance.
RBO-077 | Overview | Robo Advisory | Portfolio | Gap | Overview report.
RBO-078 | Gain/Loss | Robo Advisory | Portfolio | Gap | Gain/Loss report.
RBO-079 | Statement | Robo Advisory | Portfolio | Gap | Statement report.
RBO-080 | Orders | Robo Advisory | Portfolio | Gap | Orders report.
RBO-081 | Transfer | Robo Advisory | Portfolio | Gap | Transfer report.
RBO-082 | Market | Robo Advisory | Portfolio | Gap | Market report.
RBO-083 | Finance | Robo Advisory | Portfolio | Gap | Finance report.
RBO-084 | Disable Portfolio | Robo Advisory | Portfolio | Gap | Deactivate a portfolio.
RBO-089 | Rename Portfolio | Robo Advisory | Portfolio | Live | Rename a portfolio. |  | 2026-08-27
RBO-090 | Copy Portfolio Number | Robo Advisory | Portfolio | Live | Copy the portfolio number to clipboard. |  | 2026-08-27
RBO-091 | Hide Balance | Robo Advisory | Portfolio | Live | Mask portfolio balances on screen. |  | 2026-08-27
RBO-092 | Portfolio Analysis | Robo Advisory | Portfolio | Gap | Container: portfolio analysis and planning tools.
RBO-093 | Peer Portfolio Comparison | Robo Advisory | Portfolio | Gap | Benchmark P&L vs anonymized peers
RBO-094 | Portfolio Health Score | Robo Advisory | Portfolio | Gap | Composite quality metric (diversification + risk + perf)
RBO-095 | Allocation Tracker | Robo Advisory | Portfolio | Gap | Target vs actual allocation across markets
RBO-096 | Goal Tracker | Robo Advisory | Portfolio | Gap | Link assets to financial goals, track progress
RBO-097 | StoryTeller | Robo Advisory | Portfolio | Gap | Visual portfolio narratives (1,845 screens)
RBO-099 | Custom Index Against Benchmark | Robo Advisory | Portfolio | Gap
RBO-100 | Personal Investment Manager | Robo Advisory | Portfolio | Gap
RBO-101 | Portfolio Backtesting | Robo Advisory | Portfolio | Gap | Backtest portfolio allocation against historical market data to evaluate strategy performance.
RBO-102 | Share | Robo Advisory | Portfolio | Gap | Share a single portfolio view.
SAU-012 | Stock options | Saudi Market | Market | Planned | Full options on DOTS system | ARCD-1983, ARCD-2330
SAU-018 | Trending | Saudi Market | Market | Live | Top 20-30 most-searched stocks hourly | ARCD-41012 | 2026-08-11
SAU-025 | Volatility | Saudi Market | Market | Planned | Historical volatility indicators | ARCD-58777
SAU-038 | Market Depth | Saudi Market | Market | Live | Market depth — active traders consider non-negotiable |  | 2026-08-11
SAU-039 | Stock Screener | Saudi Market | Market | Gap | Filter stocks by fundamentals, technicals, sector
SAU-040 | Technical Analysis | Saudi Market | Market | Live | Native drawing tools, 60+ indicators, pattern detection |  | 2026-08-11
SAU-041 | Compare Stock | Saudi Market | Market | Live | Side-by-side multi-stock comparison with overlaid charts |  | 2026-08-11
SAU-045 | Major Shareholder | Saudi Market | Market | Planned | Top shareholders of listed companies
SAU-046 | Sukuk list | Saudi Market | Market | Live | Bond/Sukuk trading natively | ARCD-72385 | 2026-08-11
SAU-048 | Trade on Chart | Saudi Market | Market | Live | Place orders directly on the price chart |  | 2026-08-11
SAU-064 | Why Is It Moving | Saudi Market | Market | Gap | Screen highlighting stocks moving up in price/volume.
SAU-066 | Bulls vs Bears | Saudi Market | Market | Gap | Market sentiment view: bulls vs bears for watched stocks.
SAU-067 | News | Saudi Market | Market | Live | Market-wide news feed. | ARCD-24713, ARCD-39221 | 2026-08-11
SAU-069 | Insider Trades | Saudi Market | Market | Gap | Insider trading activity for stocks in watchlist.
SAU-070 | Government Trades | Saudi Market | Market | Gap | Government/sovereign fund trading activity for watched stocks.
SAU-076 | Analysis Changes | Saudi Market | Market | Gap | Feed of analyst rating upgrades/downgrades across the market. | ARCD-60979
SAU-095 | Market Sectors | Saudi Market | Market | Live | Filter holdings by sector/index/Shariah |  | 2026-08-11
SAU-107 | Earnings Calendar | Saudi Market | Market | Planned | Calendar view of upcoming and past company earnings announcements for Saudi-listed stocks.
SAU-110 | ETF list | Saudi Market | Market | Live | Detailed ETF profile page showing holdings, performance, dividends, and sector exposure for Saudi ETFs. |  | 2026-08-11
SAU-111 | Whale/Institutional Trades | Saudi Market | Market | Planned | Track large institutional and whale trades on Tadawul.
SAU-112 | Unusual Activity | Saudi Market | Market | Gap | Alerts for unusual trading volume or price activity on Saudi stocks.
SAU-113 | Futures Trading | Saudi Market | Market | Planned | Trading Saudi market futures and derivatives contracts.
SAU-116 | Dividend Calendar | Saudi Market | Market | Live | Dividend history, yield, and upcoming ex-dates for Saudi-listed stocks. |  | 2026-08-11
SAU-121 | AI Assistant | Saudi Market | Market | Planned | AI chat for news, charts, earnings analysis
SAU-122 | Profile | Saudi Market | Market | Live | Detailed US stock info with financials |  | 2026-08-11
SAU-123 | Stock Search | Saudi Market | Market | Live | Search by ticker/name in Arabic/English |  | 2026-08-11
SAU-124 | Sharia Stock | Saudi Market | Market | Live | General + ARC-specific Shariah filter |  | 2026-08-11
SAU-130 | Stock Dividend | Saudi Market | Market | Live | Dividend history, yield and ex-dates for the individual stock. |  | 2026-08-11
SAU-132 | Stock News | Saudi Market | Market | Live | News filtered to the individual stock. | ARCD-24713, ARCD-39221 | 2026-08-11
SAU-133 | Whale/Institutional Trades | Saudi Market | Market | Gap | Track large institutional and whale trades on Tadawul.
SAU-134 | Unusual Activity | Saudi Market | Market | Gap | Alerts for unusual trading volume or price activity on Saudi stocks.
SAU-135 | Analyst Ratings | Saudi Market | Market | Gap | Analyst buy/hold/sell ratings and price targets on the individual stock. | ARCD-60979
SAU-144 | Screener Themes | Saudi Market | Market | Gap | Save a frequently-used market filter and recall it in one tap.
SAU-190 | Market indices chart | Saudi Market | Market | Live |  |  | 2026-08-25
SAU-191 | Market Hours | Saudi Market | Market | Live |  |  | 2026-08-25
SAU-192 | Market Summary | Saudi Market | Market | Live |  |  | 2026-08-25
SAU-193 | Sector Details | Saudi Market | Market | Live |  |  | 2026-08-25
SAU-194 | Stocks | Saudi Market | Market | Live
SAU-195 | Top Gainers | Saudi Market | Market | Live |  |  | 2026-08-25
SAU-196 | Top Losers | Saudi Market | Market | Live |  |  | 2026-08-25
SAU-197 | Most Active by Quantity | Saudi Market | Market | Live |  |  | 2026-08-25
SAU-198 | Most Active by Value | Saudi Market | Market | Live |  |  | 2026-08-25
SAU-199 | Top Traders | Saudi Market | Market | Live |  |  | 2026-08-25
SAU-200 | Economic Calendar | Saudi Market | Market | Gap
SAU-202 | Trending stocks | Saudi Market | Market | Live |  |  | 2026-08-26
SAU-203 | Stock Details | Saudi Market | Market | Live
SAU-204 | Traders Summary | Saudi Market | Market | Live |  |  | 2026-08-25
SAU-205 | Key Statistics | Saudi Market | Market | Live |  |  | 2026-08-25
SAU-206 | Options Chain | Saudi Market | Market | Planned
SAU-207 | Analyst Ratings Summary | Saudi Market | Market | Gap
SAU-208 | Analyst Ratings Details | Saudi Market | Market | Gap
SAU-209 | Financial | Saudi Market | Market | Planned
SAU-210 | Statements | Saudi Market | Market | Planned
SAU-211 | Earnings | Saudi Market | Market | Planned
SAU-212 | Actions | Saudi Market | Market | Planned
SAU-213 | Holdings | Saudi Market | Market | Live |  |  | 2026-08-25
SAU-214 | Trades | Saudi Market | Market | Gap
SAU-215 | Share Stock | Saudi Market | Market | Live |  |  | 2026-08-25
SAU-216 | Add to Watchlist | Saudi Market | Market | Live |  |  | 2026-08-25
SAU-217 | Stock chart | Saudi Market | Market | Live |  |  | 2026-08-25
SAU-218 | Historical Data (Corporate Action) | Saudi Market | Market | Planned
SAU-221 | Drag and Drop Trade on Chart | Saudi Market | Market | Planned | Drag a line on the price chart to set the target price and send the order from the chart, then edit stop-loss and watch P/L without leaving it.
SAU-222 | Indices change | Saudi Market | Market | Live | Index-level movement and change for the market indices.
SAU-223 | Stock list | Saudi Market | Market | Live | Browse all listed stocks without pre-selecting an index. |  | 2026-08-25
SAU-224 | Income Statement | Saudi Market | Market | Planned | Income statement line items.
SAU-225 | Balance Sheet | Saudi Market | Market | Planned | Balance sheet line items.
SAU-226 | Cash Flow | Saudi Market | Market | Planned | Cash flow statement line items.
SAU-227 | Add Alert | Saudi Market | Market | Live | Set a price alert from the stock page. |  | 2026-08-25
SAU-228 | Stock change | Saudi Market | Market | Live | Price change for the stock, per trading session. |  | 2026-08-25
SAU-229 | Indices page | Saudi Market | Market | Live | Index detail page. |  | 2026-08-25
SAU-230 | Indices stocks | Saudi Market | Market | Planned | Constituent stocks of the index.
SAU-231 | Indices options | Saudi Market | Market | Gap | Options on the index.
SAU-232 | Trading | Saudi Market | Market | Live | Top Gainers — Trading session view. |  | 2026-08-25
SAU-235 | Trading | Saudi Market | Market | Live | Top Losers — Trading session view. |  | 2026-08-25
SAU-238 | Trading | Saudi Market | Market | Live | Most Active by Quantity — Trading session view. |  | 2026-08-25
SAU-241 | Trading | Saudi Market | Market | Live | Most Active by Value — Trading session view. |  | 2026-08-25
SAU-244 | Annual | Saudi Market | Market | Planned
SAU-245 | Quarterly | Saudi Market | Market | Planned
SAU-246 | Annual | Saudi Market | Market | Planned
SAU-247 | Quarterly | Saudi Market | Market | Planned
SAU-248 | Annual | Saudi Market | Market | Planned
SAU-249 | Quarterly | Saudi Market | Market | Planned
SAU-250 | Next report estimation | Saudi Market | Market | Planned
SAU-251 | Revenue | Saudi Market | Market | Planned
SAU-252 | EPS | Saudi Market | Market | Planned
SAU-253 | Date | Saudi Market | Market | Planned
SAU-254 | Period | Saudi Market | Market | Planned
SAU-255 | Quarterly | Saudi Market | Market | Planned
SAU-256 | Period | Saudi Market | Market | Planned
SAU-257 | Estimated | Saudi Market | Market | Planned
SAU-258 | Actual | Saudi Market | Market | Planned
SAU-259 | Surprise | Saudi Market | Market | Planned
SAU-260 | Annual | Saudi Market | Market | Planned
SAU-261 | Period | Saudi Market | Market | Planned
SAU-262 | Estimated | Saudi Market | Market | Planned
SAU-263 | Actual | Saudi Market | Market | Planned
SAU-264 | Surprise | Saudi Market | Market | Planned
SAU-265 | Revenue | Saudi Market | Market | Planned
SAU-266 | Period | Saudi Market | Market | Planned
SAU-267 | Estimated | Saudi Market | Market | Planned
SAU-268 | Actual | Saudi Market | Market | Planned
SAU-269 | Surprise | Saudi Market | Market | Planned
SAU-270 | Dividends | Saudi Market | Market | Planned
SAU-271 | Split | Saudi Market | Market | Planned
SAU-272 | Options details | Saudi Market | Market | Planned | Contract-level detail for a selected option.
SAU-273 | Analyst Ratings | Saudi Market | Market | Gap | Analyst buy/hold/sell ratings and price targets on the individual stock.
XJ-006 | News Screener | Saudi Market | Market | Gap | Personalized news dashboard with alerts | ARCD-82616
XJ-058 | Stock Key Fact | Saudi Market | Market | Gap |  | ARCD-72344
SAU-002 | Limit | Saudi Market | Orders | Live | Limit buy/sell at specified price | ARCD-1553, ARCD-87521 | 2026-08-11
SAU-007 | MOC (Market On Close) | Saudi Market | Orders | Live | Execute at official closing price | ARCD_9245 | 2026-08-11
SAU-031 | Iceberg | Saudi Market | Orders | Gap | Slicing order view
SAU-033 | Stop Loss | Saudi Market | Orders | Live | Active stop loss view | ARCD-75523 | 2026-08-11
SAU-034 | Take Profit | Saudi Market | Orders | Live | Active take profit view | ARCD-75523 | 2026-08-11
SAU-035 | Basket | Saudi Market | Orders | Live | Create basket with conditions |  | 2026-08-11
SAU-036 | Order Filter | Saudi Market | Orders | Live | Filter by status/type/market |  | 2026-08-11
SAU-042 | Conditional | Saudi Market | Orders | Live | ARC has Figma only — competitors have full production |  | 2026-08-11
SAU-044 | Quick Reorder | Saudi Market | Orders | Live | One-tap repeat previous trade — reduces friction |  | 2026-08-11
SAU-047 | Bracket | Saudi Market | Orders | Planned | Combined stop-loss + take-profit in one order
SAU-103 | Attached | Saudi Market | Orders | Planned |  | ARCD-75523
SAU-104 | Slicing | Saudi Market | Orders | Live |  | ARCD-88151, ARCD-1248 | 2026-08-11
SAU-105 | Chain | Saudi Market | Orders | Gap
SAU-106 | Trailing | Saudi Market | Orders | Gap |  | ARCD-75523
SAU-114 | Fast Order (No Confirmation) | Saudi Market | Orders | Gap | Quick order execution without confirmation dialog for experienced traders.
SAU-125 | Market | Saudi Market | Orders | Live | Buy/sell US-listed stocks (NYSE, NASDAQ) |  | 2026-08-11
SAU-126 | Options | Saudi Market | Orders | Planned | Full options on DOTS system | ARCD-1983, ARCD-2330
SAU-138 | Partial Execution | Saudi Market | Orders | Live | Display the total cost of a partially executed order including commission breakdown. | ARCD-1386 | 2026-08-15
SAU-145 | Edit | Saudi Market | Orders | Live | Modify the price, quantity, or type of a working order without cancelling and re-entering it. |  | 2026-08-16
SAU-146 | Cancel | Saudi Market | Orders | Live | Cancel a working order before execution. |  | 2026-08-16
SAU-147 | Orders History | Saudi Market | Orders | Live | Full history of past orders with status, execution detail, and date range. |  | 2026-08-16
SAU-148 | Customize Orders View | Saudi Market | Orders | Live | Customize which columns and data are displayed in the orders list. |  | 2026-08-16
SAU-149 | Convert to Market Price | Saudi Market | Orders | Live | Convert a working limit order to a market order for immediate execution. |  | 2026-08-16
SAU-219 | Order Types | Saudi Market | Orders | Live
SAU-220 | Order Details | Saudi Market | Orders | Live
SAU-020 | Portfolio P/L View | Saudi Market | Portfolio | Live | Historical performance chart | ARCD-2654 | 2026-08-11
SAU-022 | Update Avg Cost Price | Saudi Market | Portfolio | Live | Manual cost price correction | ARCD-2650 | 2026-07-16
SAU-026 | Tradable Rights | Saudi Market | Portfolio | Live | Huqooq available in portfolio |  | 2026-08-11
SAU-075 | Performance Chart | Saudi Market | Portfolio | Live | Graphical portfolio performance over time — last 3 months. | ARCD-2654 | 2026-08-11
SAU-078 | Transfer Stocks | Saudi Market | Portfolio | Live | In-specie transfer between portfolios |  | 2026-08-11
SAU-080 | Liquidate Portfolio | Saudi Market | Portfolio | Live | Bulk liquidation flow |  | 2026-08-11
SAU-081 | Reports | Saudi Market | Portfolio | Live | Portfolio reports. Sub-types: Overview, Gain/Loss, Statement, Orders, Transfer, Market, Finance. | ARCD-1720 | 2026-08-11
SAU-084 | Peer Portfolio Comparison | Saudi Market | Portfolio | Planned | Benchmark P&L vs anonymized peers | ARCD-60816
SAU-086 | Portfolio Health Score | Saudi Market | Portfolio | Planned | Composite quality metric (diversification + risk + perf) | ARCD 52378
SAU-087 | Allocation Tracker | Saudi Market | Portfolio | Planned | Target vs actual allocation across markets | ARCD-61176
SAU-090 | Goal Tracker | Saudi Market | Portfolio | Planned | Link assets to financial goals, track progress | ARCD 55733
SAU-092 | StoryTeller | Saudi Market | Portfolio | Planned | Visual portfolio narratives (1,845 screens)
SAU-098 | Auto Dividend Reinvest | Saudi Market | Portfolio | Gap | Automatic dividend reinvestment option
SAU-102 | Rights Issue | Saudi Market | Portfolio | Live | End-to-end digital rights subscription flow |  | 2026-08-11
SAU-120 | Order List | Saudi Market | Portfolio | Live | Full list of all submitted orders with status, type, and date. |  | 2026-08-11
SAU-137 | Transaction List | Saudi Market | Portfolio | Live |  |  | 2026-08-11
SAU-140 | Portfolio Backtesting | Saudi Market | Portfolio | Planned | Backtest portfolio allocation against historical market data to evaluate strategy performance. | Portfolio-Backtesting
SAU-141 | Holding Details | Saudi Market | Portfolio | Live | Dedicated screen showing one holding in detail: cost, P&L, quantity, avg price, and transactions for that stock |  | 2026-08-15
SAU-142 | Holdings | Saudi Market | Portfolio | Live | Customize what columns and data are displayed in the holdings list |  | 2026-08-15
SAU-143 | Holdings Distribution | Saudi Market | Portfolio | Live | Breakdown of holdings by sector, market, and currency |  | 2026-08-15
SAU-150 | Portfolio Dividends | Saudi Market | Portfolio | Live | Dividends received across the holdings in the portfolio. |  | 2026-08-31
SAU-151 | Today Gain | Saudi Market | Portfolio | Live | Aggregate day gain/loss across every portfolio. |  | 2026-08-16
SAU-152 | Market Value | Saudi Market | Portfolio | Live | Aggregate market value across every portfolio. |  | 2026-08-16
SAU-153 | Total Cash | Saudi Market | Portfolio | Live | Aggregate cash balance across every portfolio. |  | 2026-08-16
SAU-154 | Total Gain | Saudi Market | Portfolio | Live | Aggregate total gain/loss across every portfolio. |  | 2026-08-16
SAU-155 | All Holdings List | Saudi Market | Portfolio | Live | Consolidated holdings list spanning every portfolio. |  | 2026-08-16
SAU-156 | Holding Details | Saudi Market | Portfolio | Live | Holding detail screen reached from the consolidated holdings list. |  | 2026-08-16
SAU-157 | Orders Across All Portfolios | Saudi Market | Portfolio | Live | Orders across every portfolio in one list. |  | 2026-08-16
SAU-158 | Order Details | Saudi Market | Portfolio | Live | Order detail screen reached from the consolidated orders list. |  | 2026-08-16
SAU-159 | Holdings Distribution Across All Portfolios | Saudi Market | Portfolio | Live | Holdings distribution across every portfolio. |  | 2026-08-16
SAU-160 | Today Gain | Saudi Market | Portfolio | Live | Day gain/loss for the selected portfolio. |  | 2026-08-16
SAU-161 | Market Value | Saudi Market | Portfolio | Live | Market value of the selected portfolio. |  | 2026-08-16
SAU-162 | Total Cash | Saudi Market | Portfolio | Live | Cash balance of the selected portfolio. |  | 2026-08-16
SAU-163 | Total Gain | Saudi Market | Portfolio | Live | Total gain/loss for the selected portfolio. |  | 2026-08-16
SAU-164 | Order Details | Saudi Market | Portfolio | Live | Detail screen for a single order. |  | 2026-08-16
SAU-165 | Disable Portfolio | Saudi Market | Portfolio | Live | Deactivate a portfolio. |  | 2026-08-16
SAU-166 | Rename Portfolio | Saudi Market | Portfolio | Live | Rename a portfolio. |  | 2026-08-16
SAU-167 | Copy Portfolio Number | Saudi Market | Portfolio | Live | Copy the portfolio number to clipboard. |  | 2026-08-16
SAU-168 | Hide Balance | Saudi Market | Portfolio | Live | Mask portfolio balances on screen. |  | 2026-08-16
SAU-169 | Select Stocks | Saudi Market | Portfolio | Live | Liquidate selected holdings rather than the whole portfolio. |  | 2026-08-16
SAU-172 | Orders | Saudi Market | Portfolio | Live | Customize which columns and data are displayed in the orders list. |  | 2026-08-17
SAU-175 | Customize Holdings View | Saudi Market | Portfolio | Live | Container: customization options for the portfolio view. |  | 2026-08-17
SAU-176 | All Stocks | Saudi Market | Portfolio | Live | Liquidate every holding in the portfolio. |  | 2026-08-17
SAU-177 | Portfolio Holdings | Saudi Market | Portfolio | Live | Holdings in the selected portfolio. |  | 2026-08-17
SAU-178 | Update Avg Cost Price | Saudi Market | Portfolio | Live | Manual cost price correction, from the consolidated holding detail. |  | 2026-08-17
SAU-179 | Overview | Saudi Market | Portfolio | Live | Overview report. |  | 2026-08-17
SAU-180 | Gain/Loss | Saudi Market | Portfolio | Live | Gain/Loss report. |  | 2026-08-17
SAU-181 | Statement | Saudi Market | Portfolio | Live | Statement report. |  | 2026-08-17
SAU-182 | Orders | Saudi Market | Portfolio | Live | Orders report. |  | 2026-08-17
SAU-183 | Transfer | Saudi Market | Portfolio | Live | Transfer report. |  | 2026-08-17
SAU-184 | Market | Saudi Market | Portfolio | Live | Market report. |  | 2026-08-17
SAU-185 | Finance | Saudi Market | Portfolio | Live | Finance report. |  | 2026-08-17
SAU-186 | Portfolio Analysis | Saudi Market | Portfolio | Planned | Container: portfolio analysis and planning tools.
SAU-187 | Share | Saudi Market | Portfolio | Live | Share the consolidated all-portfolios view. |  | 2026-08-17
SAU-188 | Share | Saudi Market | Portfolio | Live | Share a single portfolio view. |  | 2026-08-17
SAU-189 | Hide Balance | Saudi Market | Portfolio | Live | Mask balances on the consolidated all-portfolios view. |  | 2026-08-17
XJ-050 | Daily Brief | Saudi Market | Portfolio | Planned |  | ARCD-72377
XJ-055 | Custom Index Against Benchmark | Saudi Market | Portfolio | Planned |  | ARCD-60887
XJ-063 | Personal Investment Manager | Saudi Market | Portfolio | Planned |  | ARCD-60444
SAU-051 | Auto-Watchlist on Buy | Saudi Market | Watchlist | Gap | Owned stocks automatically added to watchlist
SAU-057 | Watchlist | Saudi Market | Watchlist | Live | Main watchlist screen showing user's saved stocks with mini-charts and key data. |  | 2026-08-11
SAU-058 | Watchlist Story | Saudi Market | Watchlist | Planned | Story-style card view of watchlist stocks with key metrics.
SAU-060 | Watchlist — Edit / Reorder | Saudi Market | Watchlist | Live | Edit watchlist: reorder, remove, or rename watchlists. |  | 2026-08-11
SAU-136 | Multi Views | Saudi Market | Watchlist | Live |  |  | 2026-08-11
US-002 | Profile | US Trading | Market | Live | Detailed US stock info with financials | ARCD-14312 | 2026-08-11
US-003 | Sharia Stock | US Trading | Market | Live | General + ARC-specific Shariah filter | ARCD-2067 | 2026-08-11
US-004 | Stock Search | US Trading | Market | Live | Search by ticker/name in Arabic/English | ARCD-50707 | 2026-08-11
US-005 | Options | US Trading | Market | Live | Options chain with Greeks and market data | ARCD-72350, ARCD-13645 | 2026-08-11
US-008 | Government Trades | US Trading | Market | Planned | US Congress stock disclosures | ARCD-72957
US-009 | Trending | US Trading | Market | Live | High-attention US stocks | ARCD-72979 | 2026-08-11
US-012 | Stock Screener | US Trading | Market | Live | Filter US stocks by fundamentals/technicals | ARCD-61082 | 2026-08-11
US-013 | Pre/Post Market Trading | US Trading | Market | Live | Extended hours trading — baseline for US market |  | 2026-08-11
US-014 | Fractional Shares | US Trading | Market | Live | Buy partial shares of expensive stocks |  | 2026-08-11
US-015 | AI Assistant | US Trading | Market | Gap | AI chat for news, charts, earnings analysis
US-016 | Compare Stock | US Trading | Market | Live | Multi-stock side-by-side comparison |  | 2026-08-11
US-017 | ETF list | US Trading | Market | Gap | Which ETFs hold a given stock and weight
US-018 | Whale/Institutional Trades | US Trading | Market | Gap | Unusual large-volume transaction alerts
US-019 | Unusual Activity | US Trading | Market | Gap | Options/equity volume spike detection
US-020 | Bonds Trading | US Trading | Market | Gap | Fixed income trading capability
US-021 | Futures Trading | US Trading | Market | Gap | Futures product for US markets
US-025 | Major Shareholder | US Trading | Market | Gap | Institutional ownership breakdown
US-028 | Earnings Calendar | US Trading | Market | Live | Upcoming company earnings announcements |  | 2026-08-11
US-030 | Dividend Calendar | US Trading | Market | Live | Financial calendar of dividend announcements | ARCD-72987 | 2026-08-11
US-031 | Insider Trades | US Trading | Market | Planned | Executive insider trading disclosures | ARCD-68490
US-039 | Technical Analysis | US Trading | Market | Live | Full technical analysis charting with indicators and drawing tools for US stocks. |  | 2026-08-25
US-064 | Market Sectors | US Trading | Market | Gap | Filter US stocks by sector and index membership.
US-065 | Volatility | US Trading | Market | Gap | Volatility indicators by sector and exchange for US markets. | ARCD-58777
US-066 | News | US Trading | Market | Live | Market-wide news feed. |  | 2026-08-11
US-067 | Analysis Changes | US Trading | Market | Planned | Feed of analyst rating upgrades/downgrades across the market. | ARCD-60979
US-077 | Trade on Chart | US Trading | Market | Live | Execute US trades directly from the price chart interface. |  | 2026-08-11
US-098 | Sukuk list | US Trading | Market | Gap | Bond/Sukuk trading natively
US-103 | Stock Key Fact | US Trading | Market | Gap |  | ARCD-72344
US-105 | News Screener | US Trading | Market | Gap | Personalized news dashboard with alerts | ARCD-82616
US-106 | Liquidity Indicators | US Trading | Market | Live | Volume, bid-ask spread, turnover | ARCD-41013 | 2026-08-11
US-107 | Intl Indices Historical Data | US Trading | Market | Planned | Pre-aggregated index historical data | ARCD-68581
US-113 | Fractional Shares (GTN) | US Trading | Market | Gap | Buy partial shares of expensive stocks
US-116 | Stock options | US Trading | Market | Live | Options chain with Greeks and market data | ARCD-72350, ARCD-13645 | 2026-08-11
US-117 | Bulls vs Bears | US Trading | Market | Live | Bullish/bearish case via Benzinga | ARCD-61067 | 2026-08-11
US-118 | Why Is It Moving | US Trading | Market | Live | AI-driven price movement explanations | ARCD-60875 | 2026-08-11
US-119 | Government Trades | US Trading | Market | Live | US Congress stock disclosures | ARCD-72957 | 2026-08-11
US-120 | Trending stocks | US Trading | Market | Live | High-attention US stocks | ARCD-72979 | 2026-08-11
US-121 | Market Depth | US Trading | Market | Live | Market depth for US stocks |  | 2026-08-25
US-122 | Stock Dividend | US Trading | Market | Live | Dividend history, yield and ex-dates for the individual stock. | ARCD-72987 | 2026-08-11
US-123 | Insider Trades | US Trading | Market | Live | Executive insider trading disclosures | ARCD-68490 | 2026-08-11
US-124 | Stock News | US Trading | Market | Live | News filtered to the individual stock. |  | 2026-08-11
US-125 | Whale/Institutional Trades | US Trading | Market | Gap | Unusual large-volume transaction alerts
US-126 | Unusual Activity | US Trading | Market | Gap | Options/equity volume spike detection
US-127 | Analyst Ratings | US Trading | Market | Live | Consensus analyst ratings and price targets for US stocks. | ARCD-60979 | 2026-08-11
US-131 | Price Chart Corporate Actions Adjustment | US Trading | Market | Planned | Automatically adjust historical price charts for corporate actions (splits, dividends, rights issues). | ARCD-93703
US-145 | Stocks | US Trading | Market | Live
US-146 | Stock Details | US Trading | Market | Live
US-147 | Trades | US Trading | Market | Live
US-151 | Market indices chart | US Trading | Market | Live |  |  | 2026-08-25
US-152 | Market Hours | US Trading | Market | Live |  |  | 2026-08-25
US-153 | Market Summary | US Trading | Market | Live |  |  | 2026-08-25
US-154 | Sector Details | US Trading | Market | Gap
US-155 | Top Gainers | US Trading | Market | Live |  |  | 2026-08-25
US-156 | Top Losers | US Trading | Market | Live |  |  | 2026-08-25
US-157 | Most Active by Quantity | US Trading | Market | Live |  |  | 2026-08-25
US-158 | Most Active by Value | US Trading | Market | Live |  |  | 2026-08-25
US-159 | Top Traders | US Trading | Market | Live |  |  | 2026-08-25
US-160 | Screener Themes | US Trading | Market | Gap
US-162 | Traders Summary | US Trading | Market | Live |  |  | 2026-08-25
US-163 | Key Statistics | US Trading | Market | Live |  |  | 2026-08-25
US-164 | Options Chain | US Trading | Market | Live |  |  | 2026-08-25
US-165 | Analyst Ratings Summary | US Trading | Market | Live |  |  | 2026-08-25
US-166 | Analyst Ratings Details | US Trading | Market | Live |  |  | 2026-08-25
US-167 | Financial | US Trading | Market | Live
US-168 | Statements | US Trading | Market | Live |  |  | 2026-08-25
US-169 | Earnings | US Trading | Market | Live |  |  | 2026-08-25
US-170 | Actions | US Trading | Market | Live |  |  | 2026-08-31
US-171 | Holdings | US Trading | Market | Live |  |  | 2026-08-25
US-172 | Share Stock | US Trading | Market | Live |  |  | 2026-08-25
US-173 | Add to Watchlist | US Trading | Market | Live |  |  | 2026-08-25
US-174 | Stock chart | US Trading | Market | Live |  |  | 2026-08-25
US-175 | Historical Data (Corporate Action) | US Trading | Market | Gap
US-176 | Drag and Drop Trade on Chart | US Trading | Market | Gap | Drag a line on the price chart to set the target price and send the order from the chart, then edit stop-loss and watch P/L without leaving it.
US-177 | Indices change | US Trading | Market | Live | Index-level movement and change for the market indices.
US-178 | Stock list | US Trading | Market | Live | Browse all listed stocks without pre-selecting an index. |  | 2026-08-25
US-179 | Income Statement | US Trading | Market | Live | Income statement line items. |  | 2026-08-25
US-180 | Balance Sheet | US Trading | Market | Live | Balance sheet line items. |  | 2026-08-25
US-181 | Cash Flow | US Trading | Market | Live | Cash flow statement line items. |  | 2026-08-25
US-182 | Add Alert | US Trading | Market | Planned | Set a price alert from the stock page.
US-183 | Stock change | US Trading | Market | Live | Price change for the stock, per trading session. |  | 2026-08-25
US-184 | Indices page | US Trading | Market | Live | Index detail page. |  | 2026-08-25
US-185 | Indices stocks | US Trading | Market | Gap | Constituent stocks of the index.
US-186 | Indices options | US Trading | Market | Live | Options on the index. |  | 2026-08-25
US-187 | Trading | US Trading | Market | Live | Top Gainers — Trading session view. |  | 2026-08-25
US-188 | Pre | US Trading | Market | Live | Top Gainers — Pre session view. |  | 2026-08-25
US-189 | Post | US Trading | Market | Live | Top Gainers — Post session view. |  | 2026-08-25
US-190 | Trading | US Trading | Market | Live | Top Losers — Trading session view. |  | 2026-08-25
US-191 | Pre | US Trading | Market | Live | Top Losers — Pre session view. |  | 2026-08-25
US-192 | Post | US Trading | Market | Live | Top Losers — Post session view. |  | 2026-08-25
US-193 | Trading | US Trading | Market | Live | Most Active by Quantity — Trading session view. |  | 2026-08-25
US-194 | Pre | US Trading | Market | Live | Most Active by Quantity — Pre session view. |  | 2026-08-25
US-195 | Post | US Trading | Market | Live | Most Active by Quantity — Post session view. |  | 2026-08-25
US-196 | Trading | US Trading | Market | Live | Most Active by Value — Trading session view. |  | 2026-08-25
US-197 | Pre | US Trading | Market | Live | Most Active by Value — Pre session view. |  | 2026-08-25
US-198 | Post | US Trading | Market | Live | Most Active by Value — Post session view. |  | 2026-08-25
US-199 | Annual | US Trading | Market | Live |  |  | 2026-08-31
US-200 | Quarterly | US Trading | Market | Live |  |  | 2026-08-31
US-201 | Annual | US Trading | Market | Live |  |  | 2026-08-31
US-202 | Quarterly | US Trading | Market | Live |  |  | 2026-08-31
US-203 | Annual | US Trading | Market | Live |  |  | 2026-08-31
US-204 | Quarterly | US Trading | Market | Live |  |  | 2026-08-31
US-205 | Next report estimation | US Trading | Market | Live |  |  | 2026-08-25
US-206 | Revenue | US Trading | Market | Live |  |  | 2026-08-31
US-207 | EPS | US Trading | Market | Live |  |  | 2026-08-31
US-208 | Date | US Trading | Market | Live |  |  | 2026-08-31
US-209 | Period | US Trading | Market | Live |  |  | 2026-08-31
US-210 | Quarterly | US Trading | Market | Live |  |  | 2026-08-25
US-211 | Period | US Trading | Market | Live |  |  | 2026-08-31
US-212 | Estimated | US Trading | Market | Live |  |  | 2026-08-31
US-213 | Actual | US Trading | Market | Live |  |  | 2026-08-31
US-214 | Surprise | US Trading | Market | Live |  |  | 2026-08-31
US-215 | Annual | US Trading | Market | Live |  |  | 2026-08-25
US-216 | Period | US Trading | Market | Live |  |  | 2026-08-31
US-217 | Estimated | US Trading | Market | Live |  |  | 2026-08-31
US-218 | Actual | US Trading | Market | Live |  |  | 2026-08-31
US-219 | Surprise | US Trading | Market | Live |  |  | 2026-08-31
US-220 | Revenue | US Trading | Market | Live |  |  | 2026-08-25
US-221 | Period | US Trading | Market | Live |  |  | 2026-08-31
US-222 | Estimated | US Trading | Market | Live |  |  | 2026-08-31
US-223 | Actual | US Trading | Market | Live |  |  | 2026-08-31
US-224 | Surprise | US Trading | Market | Live |  |  | 2026-08-31
US-225 | Dividends | US Trading | Market | Live |  |  | 2026-08-31
US-226 | Split | US Trading | Market | Live |  |  | 2026-08-31
US-227 | Options details | US Trading | Market | Live | Contract-level detail for a selected option. |  | 2026-08-25
US-308 | Analyst Ratings | US Trading | Market | Planned | Consensus analyst ratings and price targets for US stocks.
US-309 | News and Earnings Alerts | US Trading | Market | Live |  |  | 2026-08-30
US-310 | Valuation Ratios (P/E, PEG) | US Trading | Market | Planned
US-311 | TradingView Chart | US Trading | Market | Live |  |  | 2026-08-30
US-312 | Commodities | US Trading | Market | Live |  |  | 2026-08-30
US-313 | Currencies | US Trading | Market | Gap
US-314 | Crypto | US Trading | Market | Gap
XJ-005 | Economic Calendar | US Trading | Market | Live | Global economic events and indicators | ARCD 61046 | 2026-08-11
US-001 | Market Order | US Trading | Orders | Live | Buy/sell US-listed stocks (NYSE, NASDAQ) | ARCD-70106 | 2026-08-01
US-024 | Fast Order (No Confirm) | US Trading | Orders | Gap | One-tap execution without confirmation
US-032 | Conditional Orders (US) | US Trading | Orders | Live | Support for conditional order types (if-then logic) on US market orders. | ARCD-40288 | 2026-08-11
US-033 | Stop Loss | US Trading | Orders | Live | Stop loss order type for US market positions to limit downside risk. |  | 2026-08-01
US-034 | Take Profit | US Trading | Orders | Live | Take profit order type for US market positions to lock in gains at target price. |  | 2026-08-01
US-035 | Basket Order | US Trading | Orders | Gap | Create and execute multiple US stock orders simultaneously as a basket.
US-036 | Quick Reorder (US) | US Trading | Orders | Live | One-tap reorder of previous US market trades from order history. |  | 2026-08-11
US-037 | Bracket Order (OCO) | US Trading | Orders | Live | One-cancels-other bracket orders combining stop loss and take profit for US trades. |  | 2026-08-31
US-038 | Order Filter Panel (US) | US Trading | Orders | Live | Advanced filtering panel for US market order history by status, date, and type. |  | 2026-08-11
US-040 | Market-on-Close (MOC) (US) | US Trading | Orders | Live | Market-on-close order type for US market — execute at closing auction price. |  | 2026-08-11
US-042 | Attached Order (US) | US Trading | Orders | Planned | Attached order type linking a child order to a parent order for US trades.
US-043 | Slicing Order (US) | US Trading | Orders | Live | Slicing order type to split large US orders into smaller tranches for reduced market impact. | ARCD-88151 | 2026-08-11
US-044 | Chain Order (US) | US Trading | Orders | Gap | Chain order type executing a sequence of US orders one after another.
US-045 | Trailing Order | US Trading | Orders | Live | Trailing stop order that adjusts dynamically with US stock price movement. |  | 2026-08-11
US-046 | Iceberg Order | US Trading | Orders | Gap | Iceberg order type showing only a portion of total order size for US markets.
US-099 | Limit Order | US Trading | Orders | Live | Limit buy/sell at specified price |  | 2026-08-11
US-109 | Options Order | US Trading | Orders | Live | Options chain with Greeks and market data | ARCD-72350, ARCD-13645 | 2026-08-11
US-114 | Trailing Order (GTN) | US Trading | Orders | Gap | Trailing stop order that adjusts dynamically with US stock price movement.
US-130 | Partial Execution Cost | US Trading | Orders | Live | Display the total cost of a partially executed order including commission breakdown. | ARCD-1386 | 2026-08-15
US-136 | Quick Trade Ticket | US Trading | Orders | Gap | Analyse and execute on a single screen — order ticket embedded natively in the analysis view.
US-139 | Edit Order | US Trading | Orders | Live | Modify the price, quantity, or type of a working order without cancelling and re-entering it. |  | 2026-08-16
US-140 | Cancel Order | US Trading | Orders | Live | Cancel a working order before execution. |  | 2026-08-16
US-141 | Orders History | US Trading | Orders | Live | Full history of past orders with status, execution detail, and date range. |  | 2026-08-16
US-142 | Customize Orders View | US Trading | Orders | Live | Customize which columns and data are displayed in the orders list. |  | 2026-08-16
US-143 | Convert to Market Order | US Trading | Orders | Live | Convert a working limit order to a market order for immediate execution. |  | 2026-08-16
US-148 | Order Types | US Trading | Orders | Live
US-149 | Order Details | US Trading | Orders | Live
US-315 | Bracket Order (OCO) (GTN) | US Trading | Orders | Gap
ONB-013 | Open IBKR Portfolio | US Trading | Portfolio | Live | Create International Brokerage account via IBKR | ARCD-70106, ARCD-100213 | 2026-08-11
US-048 | Instant Settlement | US Trading | Portfolio | Planned | Accelerated settlement (T+0 or T+1) for US market trades.
US-049 | Portfolio P/L View | US Trading | Portfolio | Live | Profit and loss overview for US market portfolio holdings. |  | 2026-08-11
US-050 | Update Avg Cost Price | US Trading | Portfolio | Gap | Manually adjust average cost price for US holdings to reflect transfers or corporate actions. | ARCD-2650
US-051 | Portfolio Holdings | US Trading | Portfolio | Live | Detailed view of all US market holdings with current value and quantity. |  | 2026-08-11
US-052 | Official Letter | US Trading | Portfolio | Gap | Generate and download a PDF letter of US portfolio holdings.
US-053 | Performance Chart | US Trading | Portfolio | Live | Portfolio performance chart tracking US holdings over time. |  | 2026-08-11
US-054 | Peer Portfolio Comparison | US Trading | Portfolio | Gap | Compare US portfolio performance against peer investor benchmarks. | ARCD-60816
US-056 | Portfolio Health Score | US Trading | Portfolio | Gap | Composite health score for US portfolio based on diversification, risk, and performance. | ARCD-52378
US-057 | Allocation Tracker | US Trading | Portfolio | Gap | Track US portfolio allocation vs target allocation by sector and asset class. | ARCD-61176
US-058 | Goal Tracker | US Trading | Portfolio | Gap | Track investment goals and progress for US market portfolio. | ARCD-55733
US-059 | Holdings Filter Panel | US Trading | Portfolio | Gap | Advanced filtering for US holdings by sector, performance, and holding period.
US-060 | Liquidate Portfolio | US Trading | Portfolio | Gap | One-action liquidation of selected US market holdings.
US-062 | Reports | US Trading | Portfolio | Live | Download US portfolio reports in PDF or Excel format. | ARCD-1720 | 2026-08-11
US-063 | Visual Asset Allocation | US Trading | Portfolio | Live | Visual chart showing US portfolio asset allocation breakdown. |  | 2026-08-26
US-072 | StoryTeller | US Trading | Portfolio | Gap | Narrative-driven stock summaries for US watchlist and portfolio holdings.
US-076 | Auto Dividend Reinvest | US Trading | Portfolio | Gap | Automatically reinvest US stock dividends into the same holding.
US-087 | Order List | US Trading | Portfolio | Live | Full list of all submitted orders with status, type, and date. |  | 2026-08-11
US-090 | Transfer Holdings | US Trading | Portfolio | Gap | In-specie transfer between portfolios
US-102 | Custom Index Against Benchmark | US Trading | Portfolio | Gap |  | ARCD-60887
US-104 | Personal Investment Manager | US Trading | Portfolio | Gap |  | ARCD-60444
US-108 | Daily Brief | US Trading | Portfolio | Gap |  | ARCD-72377
US-110 | Portfolio P/L View | US Trading | Portfolio | Gap | Profit and loss overview for US market portfolio holdings.
US-111 | Performance Chart | US Trading | Portfolio | Gap | Portfolio performance chart tracking US holdings over time.
US-129 | Transaction List | US Trading | Portfolio | Gap
US-132 | Portfolio Backtesting | US Trading | Portfolio | Gap | Backtest portfolio allocation against historical market data to evaluate strategy performance. | Portfolio-Backtesting
US-133 | Holding Details | US Trading | Portfolio | Live | Dedicated screen showing one holding in detail: cost, P&L, quantity, avg price, and transactions for that stock |  | 2026-08-15
US-134 | Customize Holdings View | US Trading | Portfolio | Gap | Customize what columns and data are displayed in the holdings list
US-135 | Holdings Distribution | US Trading | Portfolio | Live | Breakdown of holdings by sector, market, and currency |  | 2026-08-15
US-144 | Portfolio Dividends | US Trading | Portfolio | Planned | Dividends received across the holdings in the portfolio.
US-150 | Portfolio Analysis | US Trading | Portfolio | Gap
US-228 | Instant Settlement | US Trading | Portfolio | Planned | Accelerated settlement (T+0 or T+1) for US market trades.
US-229 | Update Avg Cost Price | US Trading | Portfolio | Gap | Manually adjust average cost price for US holdings to reflect transfers or corporate actions. | ARCD-2650
US-230 | Official Letter | US Trading | Portfolio | Gap | Generate and download a PDF letter of US portfolio holdings.
US-231 | Peer Portfolio Comparison | US Trading | Portfolio | Gap | Compare US portfolio performance against peer investor benchmarks. | ARCD-60816
US-232 | Portfolio Health Score | US Trading | Portfolio | Gap | Composite health score for US portfolio based on diversification, risk, and performance. | ARCD-52378
US-233 | Allocation Tracker | US Trading | Portfolio | Gap | Track US portfolio allocation vs target allocation by sector and asset class. | ARCD-61176
US-234 | Goal Tracker | US Trading | Portfolio | Gap | Track investment goals and progress for US market portfolio. | ARCD-55733
US-235 | Liquidate Portfolio | US Trading | Portfolio | Gap | One-action liquidation of selected US market holdings.
US-236 | Reports | US Trading | Portfolio | Planned | Download US portfolio reports in PDF or Excel format. | ARCD-1720
US-237 | Visual Asset Allocation | US Trading | Portfolio | Live | Visual chart showing US portfolio asset allocation breakdown. |  | 2026-08-26
US-238 | StoryTeller | US Trading | Portfolio | Gap | Narrative-driven stock summaries for US watchlist and portfolio holdings.
US-239 | Auto Dividend Reinvest | US Trading | Portfolio | Gap | Automatically reinvest US stock dividends into the same holding.
US-240 | Transfer Holdings | US Trading | Portfolio | Gap | In-specie transfer between portfolios
US-241 | Custom Index Against Benchmark | US Trading | Portfolio | Gap |  | ARCD-60887
US-242 | Personal Investment Manager | US Trading | Portfolio | Gap |  | ARCD-60444
US-243 | Daily Brief | US Trading | Portfolio | Gap |  | ARCD-72377
US-244 | Portfolio Backtesting | US Trading | Portfolio | Gap | Backtest portfolio allocation against historical market data to evaluate strategy performance. | Portfolio-Backtesting
US-245 | Portfolio Dividends | US Trading | Portfolio | Planned | Dividends received across the holdings in the portfolio.
US-246 | Portfolio Analysis | US Trading | Portfolio | Gap
US-247 | Portfolio Holdings | US Trading | Portfolio | Live | Detailed view of all US market holdings with current value and quantity. |  | 2026-08-26
US-248 | Holdings Filter Panel | US Trading | Portfolio | Live | Advanced filtering for US holdings by sector, performance, and holding period. |  | 2026-08-26
US-249 | Order List | US Trading | Portfolio | Live | Full list of all submitted orders with status, type, and date. |  | 2026-08-26
US-250 | Transaction List | US Trading | Portfolio | Live |  |  | 2026-08-26
US-251 | Customize Holdings View | US Trading | Portfolio | Live | Customize what columns and data are displayed in the holdings list |  | 2026-08-26
US-252 | Portfolio Holdings | US Trading | Portfolio | Live | Detailed view of all US market holdings with current value and quantity. |  | 2026-08-26
US-253 | Holdings Filter Panel | US Trading | Portfolio | Live | Advanced filtering for US holdings by sector, performance, and holding period. |  | 2026-08-26
US-254 | Order List | US Trading | Portfolio | Live | Full list of all submitted orders with status, type, and date. |  | 2026-08-26
US-255 | Transaction List | US Trading | Portfolio | Live |  |  | 2026-08-26
US-256 | Customize Holdings View | US Trading | Portfolio | Live | Customize what columns and data are displayed in the holdings list |  | 2026-08-26
US-257 | Today Gain | US Trading | Portfolio | Gap | Day gain/loss for the selected portfolio.
US-258 | Market Value | US Trading | Portfolio | Gap | Market value of the selected portfolio.
US-259 | Total Cash | US Trading | Portfolio | Gap | Cash balance of the selected portfolio.
US-260 | Total Gain | US Trading | Portfolio | Gap | Total gain/loss for the selected portfolio.
US-261 | Holding Details | US Trading | Portfolio | Gap | Dedicated screen showing one holding in detail: cost, P&L, quantity, avg price, and transactions for that stock
US-264 | Order Details | US Trading | Portfolio | Gap | Detail screen for a single order.
US-265 | Holdings Distribution | US Trading | Portfolio | Gap | Breakdown of holdings by sector, market, and currency
US-266 | Holdings | US Trading | Portfolio | Gap | Customize what columns and data are displayed in the holdings list
US-267 | Orders | US Trading | Portfolio | Gap | Customize which columns and data are displayed in the orders list.
US-268 | Overview | US Trading | Portfolio | Gap | Overview report.
US-269 | Gain/Loss | US Trading | Portfolio | Gap | Gain/Loss report.
US-270 | Statement | US Trading | Portfolio | Gap | Statement report.
US-271 | Orders | US Trading | Portfolio | Gap | Orders report.
US-272 | Transfer | US Trading | Portfolio | Gap | Transfer report.
US-273 | Market | US Trading | Portfolio | Gap | Market report.
US-274 | Finance | US Trading | Portfolio | Gap | Finance report.
US-275 | Disable Portfolio | US Trading | Portfolio | Gap | Deactivate a portfolio.
US-276 | All Stocks | US Trading | Portfolio | Gap | Liquidate every holding in the portfolio.
US-277 | Select Stocks | US Trading | Portfolio | Gap | Liquidate selected holdings rather than the whole portfolio.
US-278 | Rename Portfolio | US Trading | Portfolio | Gap | Rename a portfolio.
US-279 | Copy Portfolio Number | US Trading | Portfolio | Live | Copy the portfolio number to clipboard. |  | 2026-08-26
US-280 | Hide Balance | US Trading | Portfolio | Live | Mask portfolio balances on screen. |  | 2026-08-26
US-281 | Share | US Trading | Portfolio | Gap | Share a single portfolio view.
US-282 | Today Gain | US Trading | Portfolio | Gap | Day gain/loss for the selected portfolio.
US-283 | Market Value | US Trading | Portfolio | Gap | Market value of the selected portfolio.
US-284 | Total Cash | US Trading | Portfolio | Gap | Cash balance of the selected portfolio.
US-285 | Total Gain | US Trading | Portfolio | Gap | Total gain/loss for the selected portfolio.
US-286 | Holding Details | US Trading | Portfolio | Gap | Dedicated screen showing one holding in detail: cost, P&L, quantity, avg price, and transactions for that stock
US-289 | Order Details | US Trading | Portfolio | Gap | Detail screen for a single order.
US-290 | Holdings Distribution | US Trading | Portfolio | Gap | Breakdown of holdings by sector, market, and currency
US-291 | Holdings | US Trading | Portfolio | Gap | Customize what columns and data are displayed in the holdings list
US-292 | Orders | US Trading | Portfolio | Gap | Customize which columns and data are displayed in the orders list.
US-293 | Overview | US Trading | Portfolio | Gap | Overview report.
US-294 | Gain/Loss | US Trading | Portfolio | Gap | Gain/Loss report.
US-295 | Statement | US Trading | Portfolio | Gap | Statement report.
US-296 | Orders | US Trading | Portfolio | Gap | Orders report.
US-297 | Transfer | US Trading | Portfolio | Gap | Transfer report.
US-298 | Market | US Trading | Portfolio | Gap | Market report.
US-299 | Finance | US Trading | Portfolio | Gap | Finance report.
US-300 | Disable Portfolio | US Trading | Portfolio | Gap | Deactivate a portfolio.
US-301 | All Stocks | US Trading | Portfolio | Gap | Liquidate every holding in the portfolio.
US-302 | Select Stocks | US Trading | Portfolio | Gap | Liquidate selected holdings rather than the whole portfolio.
US-303 | Rename Portfolio | US Trading | Portfolio | Gap | Rename a portfolio.
US-304 | Copy Portfolio Number | US Trading | Portfolio | Live | Copy the portfolio number to clipboard. |  | 2026-08-26
US-305 | Hide Balance | US Trading | Portfolio | Live | Mask portfolio balances on screen. |  | 2026-08-26
US-306 | Share | US Trading | Portfolio | Gap | Share a single portfolio view.
US-307 | Hide Balance | US Trading | Portfolio | Live | Mask portfolio balances on screen. |  | 2026-08-26
US-069 | Watchlist | US Trading | Watchlist | Live | Dedicated US market watchlist with real-time prices and daily change. |  | 2026-08-11
US-070 | Watchlist Story | US Trading | Watchlist | Planned | Instagram-style story view for US watchlist stocks with key metrics.
US-081 | Auto-Watchlist on Buy (US) | US Trading | Watchlist | Gap | Automatically add US stocks to watchlist when purchased.
US-091 | Watchlist — Edit / Reorder | US Trading | Watchlist | Live | Edit watchlist: reorder, remove, or rename watchlists. |  | 2026-08-11
US-128 | Multi Views | US Trading | Watchlist | Live |  |  | 2026-08-11